## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
Phan Tiến Mạnh - HE170244 | [7 empty] | Ngô Quang Bá - HE161232
# | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated | # | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated
1 | Home page | Public | Show sliders, hot posts, featured services + the sider with the latest posts, static contacts/links | ManhPTHE170244 | To Do | iter1 | none | 1 | Service Details | Public | Show detailed service information (thumbnail, category, title, brief information, attached images, description, number of person, list price, sale price, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | BaNQHE161232 | To Do | iter1 | none
2 | User Login | Common | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | ManhPTHE170244 | To Do | iter1 | none | 2 | Reservation Details | Public | Show the cart details with list of the user's chosen services (including Id, title, price, quantity, the number of person, total cost) and the total reservation price + the sider with the service search box, service categories, static contacts/links; The user can - Change the quantity of each service: the total cost is automatically adjusted - Change the number of person taking part in a service: the total cost is automatically adjusted - Choose to delete/remove service by clicking on the deleting icon - Click the Choose More Service button to go to Services List page - Click the Check Out button to go to the Reservation Contact page Please notes: the user's chosen services from the last browsing session are remained in his/her reservation until s/he submit the cart. However, the service prices are updated with the latest prices in the system | BaNQHE161232 | To Do | iter1 | none
3 | User Authorization | Common | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) | ManhPTHE170244 | Updated | iter2 | none | 3 | Change Password | Common | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | BaNQHE161232 | Updated | iter2 | none
4 | Sliders List | Manager | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - For each slider, the user can choose to hide, show, edit it | ManhPTHE170244 | Updated | iter2 | none | 4 | Posts List | Manager | Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): - The user can filter the post by category, author, status or search by title - Sortable by title, category, author, featured, or status - From each post, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new post | BaNQHE161232 | Updated | iter2 | none
5 | Customer Details | Manager | Show the list of customers / contacts paginatedly (include contacts' id, full name, gender, email, mobile, status): - The user can filter the customers by status + search by full name, email, mobile - Sortable by full name, email, mobile, status - From each customer, the user can choose to add new, view or edit it | ManhPTHE170244 | Updated | iter2 | none | 5 | Service Details | Manager | Show detailed service information (thumbnail, category, title, brief information, attached images, description, number of person, list price, sale price, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | BaNQHE161232 | Updated | iter2 | none
6 | Medical examination | Staff | Show the history of examination including the date, used services, medical prescription Doctor can add new medical prescription; view existing medical prescription User can filter by service, date, medicine name | ManhPTHE170244 | Updated | iter3 | none | 6 | Reservations List | Staff | Show the list of reservations paginatedly - The list can be shorted by the reservation date, customer name, total cost, status - Each reservation include below information: id, reserved date, customer name,service (service name & number of person), total cost, status; - Allow the users to filter the reservation by the reservation date (from, to), status, staff - Allow the user to search the reservations by reservation id, customer name - On clicking the link under the reservation id, user would be redirected to the Reservation Details page | BaNQHE161232 | Updated | iter3 | none
7 | Setting Details | Admin | Show detailed user information (type, name, value, description, status), from that allow the user to add new, view or edit setting information | ManhPTHE170244 | Updated | iter3 | none | 7 | User Details | Admin | Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user | BaNQHE161232 | Updated | iter3 | none
8 |  |  |  | ManhPTHE170244 | Updated | iter4 | none | 8 |  |  |  | BaNQHE161232 | Updated | iter4 | none
9 |  |  |  | ManhPTHE170244 | Updated | iter4 | none | 9 |  |  |  | BaNQHE161232 | Updated | iter4 | none
Đinh Quang Công - HE160695 | [7 empty] | Nguyễn Thanh Tùng - HE161278
# | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated | # | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated
1 | Service List | Public | Show the paginated list of services (include services' id, thumbnail, title, category, list price, sale price, featured, and status information): - The user can filter the service by status or search by title, brief info - Sortable by title, category, list price, sale price, featured, or status - From each service, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new service | CongDQHE160695 | To Do | iter1 | none | 1 | Blog Details | Public | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, posts categories, static contacts/links | TungNTHE161278 | To Do | iter1 | none
2 | Feedback | Public | After the end of medical examination, the receiver would receive a confirmation email with the guides to feedback on each of the received service; Beside, the user/receive could also give the feedback (on a specific service or general feedback) via the website; The user also call this screen from the system menu on the header; The feedback information includes contact information (full name, gender, email, mobile), rated star, the attached images and the contact's free-format feedback The page sider is also shown with the service search box, service categories, static contacts/links; | CongDQHE160695 | To Do | iter1 | none | 2 | Reservation Contact | Public | Show the list of user chosen service (including id, title, price, quantity, total cost), the total reservation price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the service search box, service categories, static contacts/links - In case the user has logged in, the receiver information would be filled with the user's information - The user can click the Change button to come back to the Reservation Details page for changing the choosing servicds, click the Submit button to submit the reservation before redirecting user to the Reservation Completion or Error page (due to technical error or the time is out of the slot) | TungNTHE161278 | To Do | iter1 | none
3 | Reset Password | Common | The user input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | CongDQHE160695 | Updated | iter2 | none | 3 | User Profile | Common | This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email | TungNTHE161278 | Updated | iter2 | none
4 | Reservation Information | Customer | Show the reservation details, including the information as below + the sider with the post search box, posts categories, static contacts/links - The reservation id, reservation date, time to check up, total cost, status - The receiver information: full name, gender, email, mobile - This list of reserved services, each service include following information & the links/buttons that allow the user to re-reserve or feedback: thumbnail, name, service, unit price, number of person, total cost For the submitted reservation, the user can choose to update (redirect the user to the Reservation Details page for that) or cancel the reservation | CongDQHE160695 | Updated | iter2 | none | 4 | Post Details | Manager | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | TungNTHE161278 | Updated | iter2 | none
5 | Services List | Manager | Show the paginated list of services (include services' id, thumbnail, title, category, list price, sale price, featured, and status information): - The user can filter the service by status or search by title, brief info - Sortable by title, category, list price, sale price, featured, or status - From each service, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new service | CongDQHE160695 | Updated | iter2 | none | 5 | Customers List | Manager | Show the list of customers / contacts paginatedly (include contacts' id, full name, gender, email, mobile, status): - The user can filter the customers by status + search by full name, email, mobile - Sortable by full name, email, mobile, status - From each customer, the user can choose to add new, view or edit it | TungNTHE161278 | Updated | iter2 | none
6 | Feedback Details | Manager | Show the feedback details (contact full name, email, mobile, service, rated star, feedback, images status) from that allow the user to change its status | CongDQHE160695 | Updated | iter3 | none | 6 | Rerservation Details | Staff | Show the reservation details, including the following information: - Basic reservation information: reservation id, customer full name, email, mobile, reservation date, total cost, sale name, status - The receiver information: full name, gendar, email, mobile, address - This list of reserved services, each service include following information: thumbnail, name, category, unit price, number of person, total cost Manager can change the reservation status Manager can assign the reservation to other staffs | TungNTHE161278 | Updated | iter3 | none
7 | Users List | Admin | Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user | CongDQHE160695 | Updated | iter3 | none | 7 | Settings List | Admin | Show the paginated list of settings (include settings' id, type, name, value, status): - The admin can filter the setting by type, status - Allow the admin to seach settings by name, value - The list is sortable by id, type, name, value, status - From each setting, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new setting | TungNTHE161278 | Updated | iter3 | none
8 |  |  |  | CongDQHE160695 | Updated | iter4 | none | 8 |  |  |  | TungNTHE161278 | Updated | iter4 | none
9 |  |  |  | CongDQHE160695 | Updated | iter4 | none | 9 |  |  |  | TungNTHE161278 | Updated | iter4 | none
Đoàn Đắc Hậu - HE160776
# | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated
26 | Blog List | Public | Show the posts paginatedly (sorted by updated date, paginated) + the sider with the post search box, posts categories, static contacts/links; Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking | HauDDHE160776 | To Do | iter1 | none
27 | Reservation Completion | Public | This page show the cart completion notes + the sider with the service search box, service categories, static contacts/links; Before this page is shown: - The reservation status is changed to submitted; - The service's available quantities are updated accordingly - The submitted reservation is assigned automatically to the active nurse, doctor rotatedly or the doctor & nurse are chosen by customers - If the receiver information (name, email, mobile, gender) is new or changed (checking via the email, the latest receiver information is stored in the system as latest & historical system contact information (for the marketing's reference later) - The customer/user would be received the reservation confirmation & payment guides via his/her email. Those information is shown on the page also. The payment information (banking account,...) are taken from the system configuration file | HauDDHE160776 | To Do | iter1 | none
28 | User Register | Common | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile, and address; User then need to verify by clicking the link sent via email to him/her before being able to access the system | HauDDHE160776 | Updated | iter2 | none
29 | My reservations | Customer | Show the list of user's reservations paginatedly + the sider with the post search box, posts categories, static contacts/links - Each reservation include below information: id, reserved date, service (first service name & number of persons), time to check up, total cost, status; - On clicking the link under the reservation id, user would be redirected to the Reservation Information page | HauDDHE160776 | Updated | iter2 | none
5 | Slider Details | Manager | Show detailed slider information (image, title, backlink, status, notes) | HauDDHE160776 | Updated | iter2 | none
6 | Feedbacks List | Manager | Show the list of feedbacks paginatedly (include feedbacks' contact full name, service name, rated star, status): - The user can filter the feedbacks by status, service, rated star + search by full name, feedback content - Sortable by full name, service name, rated star, status - From each feedback, the user can choose to view or change it's status | HauDDHE160776 | Updated | iter3 | none
7 | Admin Dashboard | Admin | Show statistics of new reservations (success, cancelled, submitted), revenues (total, by service categories), customers (newly registered, newly reserved), feedbacks (average star: total, by service) & the trend of reservation counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | HauDDHE160776 | Updated | iter3 | none
8 |  |  |  | HauDDHE160776 | Updated | iter4 | none
9 |  |  |  | HauDDHE160776 | Updated | iter4 | none

## Iter1
STT | Công việc cần làm | Feature | Người chịu trách nghiệm | Trạng thái | Deadline | Ngày nhận việc | QUY TẮC LÀM VIỆC CỦA NHÓM 1.Mọi thành viên phải đăng ký account trên git hub bằng mail fpt.edu.vn 2.Tất cả thành viên phải thiết kế giao diện screen của mình trên figma 3.Mọi thành viên đều phải code 4.Các thành viên đều có nhiệm vụ đào tạo cho nhau để viết doc, code được. 5.Ai có khó khăn phải chia sẻ ngay với nhóm hoặc thầy 6. Tất cả các thành viên trong nhóm đều có cấu trúc thư mục dự án giống như thầy đã hướng dẫn. TL có trách nhiệm kiểm tra thành viên trong nhóm có cấu trúc thư mục như thầy hướng dẫn chưa và báo cáo vào nhóm. 7. TL tổ chức training các thành viên qua Ggmeet. Record lại buổi họp để chứng minh các thành viên đều được training và có tham gia 8. Không thể dựa vào trí nhớ của các thành viên mà hãy dựa vào các công cụ ghi chép : node, record,... để làm thành tài liệu, video tham khảo. 9. Mỗi tuần có 2 lần họp chính vào chủ nhật và thứ 5, nếu buổi học trên lớp các thành viên không đi đủ để thảo luận hoặc không có thời gian thảo luận trên lớp, tối hôm đó sẽ họp để tiến hành phân công nhiệm vụ, giờ họp cố định là 9h. 10. Nhiệm vụ được phân công cần được chia nhỏ theo ngày với deadline là 10h hằng ngày, mỗi khi xong nhiệm vụ thành viên cần thay đổi trạng thái nhiệm vụ thành chờ test, nhóm trưởng sẽ kiểm tra và thay đổi trạng thái thành đã hoàn thành hoặc fixing tùy theo mức độ hoàn thiện.
1 | Upload video meeting |  | Mạnh | Done | 15/05/2023 | 15/05/2023
2 | Upload git hub |  | Mạnh | Done | 15/05/2023 | 15/05/2023
3 | Học làm SRS và SDS và làm mẫu nộp cho thầy |  | Tú Anh | Done | 15/05/2023 | 15/05/2023
4 | Training thiết kế figma |  | Sơn | Done | 15/05/2023 | 15/05/2023
5 | Code JSP cho CourseList và CourseDetail |  | Tú Anh | Done | 16/05/2023 | 15/05/2023
6 | Tạo entity cho HomePage |  | Linh | Done | 16/05/2023 | 15/05/2023
7 | Tạo DAO cho HomePage |  | Linh | Done | 16/05/2023 | 15/05/2023
8 | Làm giao diện đăng ký |  | Sơn | Done | 16/05/2023 | 15/05/2023
9 | Làm entity và DAO cho đăng ký |  | Sơn | Done | 16/05/2023 | 15/05/2023
10 | Code servlet cho đăng ký |  | Sơn | Done | 16/05/2023 | 15/05/2023
11 | Code JSP cho login |  | Quốc Anh | Done | 16/05/2023 | 15/05/2023
12 | Vẽ flow chart |  | Sơn | Fixing | 17/05/2023 | 15/05/2023
13 | Phổ biến database cho mọi người |  | Mạnh | Done | 17/05/2023 | 15/05/2023
14 | Làm servlet cho HomePage |  | Mạnh | Done | 17/05/2023 | 15/05/2023
15 | Điền thông tin vào gg sheet project tracking |  | Linh | Done | 17/05/2023 | 15/05/2023
16 | Viết tài liệu SRS cho phần mình làm |  | Cả nhóm | Doing | 17/05/2023 | 15/05/2023
17 | Viết tài liệu SDS cho phần mình làm |  | Cả nhóm | Doing | 17/05/2023 | 15/05/2023
18 | Code DAO và entity cho login |  | Quốc Anh | Done | 17/05/2023 | 15/05/2023
19 | Code servlet cho login |  | Quốc Anh | Done | 17/05/2023 | 15/05/2023
20 | Làm enity và DAO cho BlogList và BlogDetails |  | Linh | Done | 17/05/2023 | 15/05/2023
21 | Training SRS và SDS |  | Tú Anh | Done | 17/05/2023 | 15/05/2023
22 | Làm servlet cho CourseDetail và CourseList |  | Mạnh | Fixing | 18/05/2023 | 15/05/2023
23 | Làm servlet với JSP cho User Profile |  | Sơn | Done | 18/05/2023 | 15/05/2023
24 | Làm reset servlet và JSP cho reset password |  | Quốc Anh | Testing | 18/05/2023 | 15/05/2023
25 | Làm JSP cho BlogList và BlogDetails |  | Tú Anh | Doing | 18/05/2023 | 15/05/2023
26 | Đọc tài liệu code convention |  | Linh | Doing | 18/05/2023 | 15/05/2023
27 | Làm reset servlet và JSP cho change password |  | Quốc Anh | Testing | 19/05/2023 | 15/05/2023
28 | Làm servlet cho PostDetail và PostList |  | Mạnh | Fixing | 19/05/2023 | 15/05/2023
29 | Authorization |  | Sơn | To Do | 23/05/2023 | 15/05/2023
30 | Xem lại git hub xem còn lỗi không, phổ biến cách sửa lỗi nếu gặp phải, thêm phần private với build vào git ignore |  | Cả nhóm | To Do | 22/05/2023 | 21/05/2023
31 | Xem lại file Function Details xem còn function nào mô tả sai không, và nghĩ thêm function mới |  | Mạnh | To Do | 22/05/2023 | 21/05/2023
32 | Sửa và làm database trở nên hoàn hảo |  | Sơn | To Do | 26/05/2023 | 21/05/2023
33 | Nhập dữ liệu vào database |  | Mạnh | To Do | 27/05/2023 | 21/05/2023
34 | Hướng dẫn đồng bộ hóa template |  | Cả nhóm | To Do | 22/05/2023 | 21/05/2023
35 | Tìm hiểu SRS và SDS |  | Cả nhóm | To Do | 25/05/2023 | 21/05/2023
36 | Vẽ figma |  | Linh | To Do | 23/05/2023 | 21/05/2023
37 | Làm SRS và SDS |  | Quốc Anh | To Do | 26/05/2023 | 21/05/2023
To do
Done
Doing

## Iter2
STT | Screen | Feature | Người chịu trách nghiệm | Trạng thái | Deadline | QUY TẮC LÀM VIỆC CỦA NHÓM 1.Mọi thành viên phải đăng ký account trên git hub bằng mail fpt.edu.vn 2.Tất cả thành viên phải thiết kế giao diện screen của mình trên figma 3.Mọi thành viên đều phải code 4.Các thành viên đều có nhiệm vụ đào tạo cho nhau để viết doc, code được. 5.Ai có khó khăn phải chia sẻ ngay với nhóm hoặc thầy 6. Tất cả các thành viên trong nhóm đều có cấu trúc thư mục dự án giống như thầy đã hướng dẫn. TL có trách nhiệm kiểm tra thành viên trong nhóm có cấu trúc thư mục như thầy hướng dẫn chưa và báo cáo vào nhóm. 7. TL tổ chức training các thành viên qua Ggmeet. Record lại buổi họp để chứng minh các thành viên đều được training và có tham gia 8. Không thể dựa vào trí nhớ của các thành viên mà hãy dựa vào các công cụ ghi chép : node, record,... để làm thành tài liệu, video tham khảo. 9. Mỗi tuần có 2 lần họp chính vào chủ nhật và thứ 5, nếu buổi học trên lớp các thành viên không đi đủ để thảo luận hoặc không có thời gian thảo luận trên lớp, tối hôm đó sẽ họp để tiến hành phân công nhiệm vụ, giờ họp cố định là 9h. 10. Nhiệm vụ được phân công cần được chia nhỏ theo ngày với deadline là 10h hằng ngày, mỗi khi xong nhiệm vụ thành viên cần thay đổi trạng thái nhiệm vụ thành chờ test, nhóm trưởng sẽ kiểm tra và thay đổi trạng thái thành đã hoàn thành hoặc fixing tùy theo mức độ hoàn thiện.
To do
Done
Doing

## Iter3
STT | Screen | Feature | Người chịu trách nghiệm | Trạng thái | Deadline | QUY TẮC LÀM VIỆC CỦA NHÓM 1.Mọi thành viên phải đăng ký account trên git hub bằng mail fpt.edu.vn 2.Tất cả thành viên phải thiết kế giao diện screen của mình trên figma 3.Mọi thành viên đều phải code 4.Các thành viên đều có nhiệm vụ đào tạo cho nhau để viết doc, code được. 5.Ai có khó khăn phải chia sẻ ngay với nhóm hoặc thầy 6. Tất cả các thành viên trong nhóm đều có cấu trúc thư mục dự án giống như thầy đã hướng dẫn. TL có trách nhiệm kiểm tra thành viên trong nhóm có cấu trúc thư mục như thầy hướng dẫn chưa và báo cáo vào nhóm. 7. TL tổ chức training các thành viên qua Ggmeet. Record lại buổi họp để chứng minh các thành viên đều được training và có tham gia 8. Không thể dựa vào trí nhớ của các thành viên mà hãy dựa vào các công cụ ghi chép : node, record,... để làm thành tài liệu, video tham khảo. 9. Mỗi tuần có 2 lần họp chính vào chủ nhật và thứ 5, nếu buổi học trên lớp các thành viên không đi đủ để thảo luận hoặc không có thời gian thảo luận trên lớp, tối hôm đó sẽ họp để tiến hành phân công nhiệm vụ, giờ họp cố định là 9h. 10. Nhiệm vụ được phân công cần được chia nhỏ theo ngày với deadline là 10h hằng ngày, mỗi khi xong nhiệm vụ thành viên cần thay đổi trạng thái nhiệm vụ thành chờ test, nhóm trưởng sẽ kiểm tra và thay đổi trạng thái thành đã hoàn thành hoặc fixing tùy theo mức độ hoàn thiện.
1 |  |  |  | To do
2 |  |  |  | To do
3 |  |  |  | To do
4 |  |  |  | To do
5 |  |  |  | To do
6 |  |  |  | To do
7 |  |  |  | To do
8 |  |  |  | To do
9 |  |  |  | To do
10 |  |  |  | To do
11 |  |  |  | To do
12 |  |  |  | To do
13 |  |  |  | To do
14 |  |  |  | To do
15 |  |  |  | To do
16 |  |  |  | To do
17 |  |  |  | To do
18 |  |  |  | To do
19 |  |  |  | To do
20 |  |  |  | To do
To do
Done
Doing

## Iter4
STT | Screen | Feature | Người chịu trách nghiệm | Trạng thái | Deadline | QUY TẮC LÀM VIỆC CỦA NHÓM 1.Mọi thành viên phải đăng ký account trên git hub bằng mail fpt.edu.vn 2.Tất cả thành viên phải thiết kế giao diện screen của mình trên figma 3.Mọi thành viên đều phải code 4.Các thành viên đều có nhiệm vụ đào tạo cho nhau để viết doc, code được. 5.Ai có khó khăn phải chia sẻ ngay với nhóm hoặc thầy 6. Tất cả các thành viên trong nhóm đều có cấu trúc thư mục dự án giống như thầy đã hướng dẫn. TL có trách nhiệm kiểm tra thành viên trong nhóm có cấu trúc thư mục như thầy hướng dẫn chưa và báo cáo vào nhóm. 7. TL tổ chức training các thành viên qua Ggmeet. Record lại buổi họp để chứng minh các thành viên đều được training và có tham gia 8. Không thể dựa vào trí nhớ của các thành viên mà hãy dựa vào các công cụ ghi chép : node, record,... để làm thành tài liệu, video tham khảo. 9. Mỗi tuần có 2 lần họp chính vào chủ nhật và thứ 5, nếu buổi học trên lớp các thành viên không đi đủ để thảo luận hoặc không có thời gian thảo luận trên lớp, tối hôm đó sẽ họp để tiến hành phân công nhiệm vụ, giờ họp cố định là 9h. 10. Nhiệm vụ được phân công cần được chia nhỏ theo ngày với deadline là 10h hằng ngày, mỗi khi xong nhiệm vụ thành viên cần thay đổi trạng thái nhiệm vụ thành chờ test, nhóm trưởng sẽ kiểm tra và thay đổi trạng thái thành đã hoàn thành hoặc fixing tùy theo mức độ hoàn thiện.
1 |  |  |  | To do
2 |  |  |  | To do
3 |  |  |  | To do
4 |  |  |  | To do
5 |  |  |  | To do
6 |  |  |  | To do
7 |  |  |  | To do
8 |  |  |  | To do
9 |  |  |  | To do
10 |  |  |  | To do
11 |  |  |  | To do
12 |  |  |  | To do
13 |  |  |  | To do
14 |  |  |  | To do
15 |  |  |  | To do
16 |  |  |  | To do
17 |  |  |  | To do
18 |  |  |  | To do
19 |  |  |  | To do
20 |  |  |  | To do
To do
Done
Doing