## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
Phan Tiến Mạnh - HE170244 | [7 empty] | Phan Nguyễn Tú Anh - HE163972
# | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated | # | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated
1 | Post Details | Public | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, posts categories, latest posts, static contacts/links | ManhPTHE170244 | Done | iter1 | none | 1 | Home | Public | Show sliders, hot posts, featured subjects + the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, post date; the user is redirected to the post's details on his/her clicking - Shown subject information includes its thumbnail, title, tag line; the user is redirected to the subjectt's details on his/her clicking | AnhPNTHE163972 | Done | iter1 | none
2 | Courses List | Public | Show the subjects paginatedly (sorted by updated date, paginated) + the sider with the subject search box, subject categories, featured subjects, and static contacts/links; - Shown subject information includes its thumbnail, title, tag line, lowest price package option (list price, sale price); - The user is redirected to the subject's details on his/her clicking on the subject - The user can choose to register to the subject by clicking the Register button | ManhPTHE170244 | Done | iter1 | none | 2 | Posts List | Public | Show the posts paginatedly (sorted by updated date) + the sider with the post search box, posts categories, latest posts, static contacts/links; Shown post information includes its thumbnail, title, category, brief-info; the user is redirected to the post's details on his/her clicking | AnhPNTHE163972 | Done | iter1 | none
3 | Pakage Register | Public | This is a pop-up screen which allow the user to update account | ManhPTHE170244 | Done | iter2 |  | 3 | Quiz Lesson | Customer | This allows the user to take the topic quiz or view the quiz results | AnhPNTHE163972 | Done | iter2
4 | Quiz Handle | Learning | This screen allows the user to browse and answer the quiz questions and flag the important question for review | ManhPTHE170244 | Done | iter2 |  | 4 | Sliders List Edit | Marketing | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - For each slider, the user can choose to hide, show, edit it | AnhPNTHE163972 | Done | iter2
5 | Courses List Edit | Course Content | Show the list of course lecturers created. The shown information for each subject include the id, name, category, number of lessons, owner, and status The user can: - Filter the list by course category & status. - Search the course by the name. - Choose to add a new course (redirect the user to the New Subject page for that). - Edit course information (linked to the Subject Details for that). | ManhPTHE170244 | Done | iter3 |  | 5 | Course Details Edit | Course Content | This page allows the admin and the assigned expert to access and prepare the subject information, including the course general information, the dimension, and price package. Only the admin can change the status to Published or Unpublished + add/edit the price packages. | AnhPNTHE163972 | Done | iter3
6 | Course Details Edit | Course Content | The screen is shown with below information for the user to input new course information: name, thumbnail image, category, featured flag, owner, status, and description. | ManhPTHE170244 | Done | iter3 |  | 6 | Price Package Edit | Course Content | This page allows the admin and sales to edit Price Package dimensions (Name, multiplier, duration, …) | AnhPNTHE163972 | Done | iter3
7 | Lesson List Edit | Course Content | This page allows the admin/lecturer to input/edit the lesson information | ManhPTHE170244 | Done | iter4 |  | 7 | PostCategoryEdit | Marketing |  | AnhPNTHE163972 | Done | iter4
8 |  |  |  | ManhPTHE170244 |  | iter4 |  | 8
9 |  |  |  | ManhPTHE170244 |  |  |  | 9
Chu Quý Sơn - HE170808 | [7 empty] | Nguyễn Thị Ngọc Linh - HE171088
# | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated | # | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated
1 | User Login | Common | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | SonCQHE170808 | Done | iter1 | none | 1 | User Profile | Common | This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email | LinhNTNHE171088 | Done | iter1 | none
2 | User Register | Common | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile; User then need to verify by clicking the link sent via email to him/her before being able to access the system | SonCQHE170808 | Done | iter1 | none | 2 | Change Password | Common | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | LinhNTNHE171088 | Done | iter1 | none
3 | My Courses | Customer | for the customer to view his/her access-allowed courses | SonCQHE170808 | Done | iter2 |  | 3 | Slider Details Edit | Marketing | Show detailed slider information (image, title, backlink, status, notes) | LinhNTNHE171088 | Done | iter2
4 | Dashboard | Marketing | Show statistics of new subjects (new, all), revenues (total, by subject categories), customers (newly bought), and the trend of order counts by day for the last 7 days (the start date & end date can be adjustable) | SonCQHE170808 | Done | iter2 |  | 4 | Post Details Edit | Marketing | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | LinhNTNHE171088 | Done | iter2
5 | Course Lessons Edit | Course Content | This page shows the list of lessons for a selected package. On this page, the admin/expert is allowed to activate/deactivate, or call the Lesson Details for adding new or editing existing lesson | SonCQHE170808 | Done | iter3 |  | 5 | Questions List Edit | Test Content | The existing questions list for a specific subject/course are shown here (paginated). On this screen, the admin/expert is allowed to filter the questions by the subject, lesson, dimension(s), level, status + search the questions by content Below information is shown for each question in the list: id, content, subject /dimension /lesson, level, status + options to show, hide, edit it; The page also allows the user to import the question (redirect him/her to the Questions Import pop-up screen. | LinhNTNHE171088 | Done | iter3
6 | Quiz Content edit | Test Content | This screen allow users to input, edit, delete the content of a quiz lesson. The user can also import the question and answer from a file | SonCQHE170808 | Done | iter3 |  | 6 | Question Details Edit | Test Content | This page allows the admin/expert to input or edit questions information, including following information: subject, dimension(s), lesson, status, content, media (image, audio, video – with preview option), answer options (with the key marked + ability to add, edit, delete), and explanation. | LinhNTNHE171088 | Done | iter3
7 | Deposit | Sale Feature |  | SonCQHE170808 | Done | iter4 |  | 7 | SubjectEdit | Marketing |  | LinhNTNHE171088 | Done | iter4
8 |  |  |  | SonCQHE170808 |  | iter4 |  | 8 |  |  |  | LinhNTNHE171088 |  | iter4
9 |  |  |  | SonCQHE170808 |  |  |  | 9
Võ Quốc Anh - HE153742
# | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated
26 | Reset Password | Common | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | AnhVQHE153742 | Done | iter1 | none
27 | User Authorization | Common | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) | AnhVQHE153742 | Done | iter1 | none
28 | Lesson View | Customer | allow customer to access the course lessons for his/her studying | AnhVQHE153742 | Done | iter2
29 | Lesson List | Learning | This screen alows the user to view lesson list | AnhVQHE153742 | Done | iter2
5 | Quizzes List Edit | Test Content | The existing questions list for a specific subject/course are shown here (paginated). On this screen, the admin/expert is allowed to filter the questions by the subject, lesson, dimension(s), level, status + search the questions by content Below information is shown for each question in the list: id, content, subject /dimension /lesson, level, status + options to show, hide, edit it; The page also allows the user to import the question (redirect him/her to the Questions Import pop-up screen. | AnhVQHE153742 | Done | iter3
6 | Test statistic | Test Content | This page allows the user to see the statistic of a test based on the score of 0 - 10 | AnhVQHE153742 | Done | iter3
7 | Lecturer Dashboard | Sale Feature |  | AnhVQHE153742 | Done | iter4
8 | [5 empty] | iter4
9

## Iter1
STT | Công việc cần làm | Feature | Người chịu trách nghiệm | Trạng thái | Deadline | Ngày nhận việc | QUY TẮC LÀM VIỆC CỦA NHÓM 1.Mọi thành viên phải đăng ký account trên git hub bằng mail fpt.edu.vn 2.Tất cả thành viên phải thiết kế giao diện screen của mình trên figma 3.Mọi thành viên đều phải code 4.Các thành viên đều có nhiệm vụ đào tạo cho nhau để viết doc, code được. 5.Ai có khó khăn phải chia sẻ ngay với nhóm hoặc thầy 6. Tất cả các thành viên trong nhóm đều có cấu trúc thư mục dự án giống như thầy đã hướng dẫn. TL có trách nhiệm kiểm tra thành viên trong nhóm có cấu trúc thư mục như thầy hướng dẫn chưa và báo cáo vào nhóm. 7. TL tổ chức training các thành viên qua Ggmeet. Record lại buổi họp để chứng minh các thành viên đều được training và có tham gia 8. Không thể dựa vào trí nhớ của các thành viên mà hãy dựa vào các công cụ ghi chép : node, record,... để làm thành tài liệu, video tham khảo. 9. Mỗi tuần có 2 lần họp chính vào chủ nhật và thứ 5, nếu buổi học trên lớp các thành viên không đi đủ để thảo luận hoặc không có thời gian thảo luận trên lớp, tối hôm đó sẽ họp để tiến hành phân công nhiệm vụ, giờ họp cố định là 9h. 10. Nhiệm vụ được phân công cần được chia nhỏ theo ngày với deadline là 10h hằng ngày, mỗi khi xong nhiệm vụ thành viên cần thay đổi trạng thái nhiệm vụ thành chờ test, nhóm trưởng sẽ kiểm tra và thay đổi trạng thái thành đã hoàn thành hoặc fixing tùy theo mức độ hoàn thiện.
1 | User Login | Common | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | SonCQHE170808 | 21/05/2023 | 2023-07-05
2 | User Register | Common | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile; User then need to verify by clicking the link sent via email to him/her before being able to access the system | SonCQHE170808 | 21/05/2023 | 2023-07-05
3 | Reset Password | Common | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | AnhVQHE153742 | 21/05/2023 | 2023-07-05
4 | Change Password | Common | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | AnhVQHE153742 | 21/05/2023 | 2023-07-05
5 | User Profile | Common | This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email | LinhNTNHE171088 | 21/05/2023 | 2023-07-05
6 | Courses Details | Public | Show subject details (including title, tag line, brief info, lowest price package option (original price, sale price), product description, and a Register button) + the slider with the subject search box, subject categories, featured subjects, static contacts/links | LinhNTNHE171088 | 21/05/2023 | 2023-07-05
7 | Home | Public | Show sliders, hot posts, featured subjects + the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, post date; the user is redirected to the post's details on his/her clicking - Shown subject information includes its thumbnail, title, tag line; the user is redirected to the subjectt's details on his/her clicking | AnhPNTHE163972 | 21/05/2023 | 2023-07-05
8 | Posts List | Public | Show the posts paginatedly (sorted by updated date) + the sider with the post search box, posts categories, latest posts, static contacts/links; Shown post information includes its thumbnail, title, category, brief-info; the user is redirected to the post's details on his/her clicking | AnhPNTHE163972 | 21/05/2023 | 2023-07-05
9 | Post Details | Public | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, posts categories, latest posts, static contacts/links | ManhPTHE170244 | 21/05/2023 | 2023-07-05
10 | Courses List | Public | Show the subjects paginatedly (sorted by updated date, paginated) + the sider with the subject search box, subject categories, featured subjects, and static contacts/links; - Shown subject information includes its thumbnail, title, tag line, lowest price package option (list price, sale price); - The user is redirected to the subject's details on his/her clicking on the subject - The user can choose to register to the subject by clicking the Register button | ManhPTHE170244 | 21/05/2023 | 2023-07-05
To do
Done
Doing

## Iter2
STT | Screen | Feature | Người chịu trách nghiệm | Trạng thái | Deadline | Ngày nhận việc | QUY TẮC LÀM VIỆC CỦA NHÓM 1.Mọi thành viên phải đăng ký account trên git hub bằng mail fpt.edu.vn 2.Tất cả thành viên phải thiết kế giao diện screen của mình trên figma 3.Mọi thành viên đều phải code 4.Các thành viên đều có nhiệm vụ đào tạo cho nhau để viết doc, code được. 5.Ai có khó khăn phải chia sẻ ngay với nhóm hoặc thầy 6. Tất cả các thành viên trong nhóm đều có cấu trúc thư mục dự án giống như thầy đã hướng dẫn. TL có trách nhiệm kiểm tra thành viên trong nhóm có cấu trúc thư mục như thầy hướng dẫn chưa và báo cáo vào nhóm. 7. TL tổ chức training các thành viên qua Ggmeet. Record lại buổi họp để chứng minh các thành viên đều được training và có tham gia 8. Không thể dựa vào trí nhớ của các thành viên mà hãy dựa vào các công cụ ghi chép : node, record,... để làm thành tài liệu, video tham khảo. 9. Mỗi tuần có 2 lần họp chính vào chủ nhật và thứ 5, nếu buổi học trên lớp các thành viên không đi đủ để thảo luận hoặc không có thời gian thảo luận trên lớp, tối hôm đó sẽ họp để tiến hành phân công nhiệm vụ, giờ họp cố định là 9h. 10. Nhiệm vụ được phân công cần được chia nhỏ theo ngày với deadline là 10h hằng ngày, mỗi khi xong nhiệm vụ thành viên cần thay đổi trạng thái nhiệm vụ thành chờ test, nhóm trưởng sẽ kiểm tra và thay đổi trạng thái thành đã hoàn thành hoặc fixing tùy theo mức độ hoàn thiện.
| Quiz Review | Learning | This screen allows the user to review the details of the quiz that s/he has just taken, and the user can see flag questions. | SonCQHE170808 | 2023-10-06 | 22/05/2023
| Dashboard | Marketing | Show statistics of new subjects (new, all), revenues (total, by subject categories), customers (newly bought), and the trend of order counts by day for the last 7 days (the start date & end date can be adjustable) | SonCQHE170808 | 2023-10-06 | 22/05/2023
| Pakage Register | Sale | This is a pop-up screen which allow the user to update account | ManhPTHE170244 | 2023-10-06 | 22/05/2023
| Quiz Handle | Learning | This screen allows the user to browse and answer the quiz questions and flag the important question for review | ManhPTHE170244 | 2023-10-06 | 22/05/2023
| Quiz Lesson | Learning | This allows the user to take the topic quiz or view the quiz results | AnhPNTHE163973 | 2023-10-06 | 22/05/2023
| Sliders List Edit | Marketing | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - For each slider, the user can choose to hide, show, edit it | AnhPNTHE163974 | 2023-10-06 | 22/05/2023
| Slider Details Edit | Marketing | Show detailed slider information (image, title, backlink, status, notes) | LinhNTNHE171088 | 2023-10-06 | 22/05/2023
| Post Details Edit | Marketing | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | LinhNTNHE171088 | 2023-10-06 | 22/05/2023
| Lesson View | Learning | allow customer to access the course lessons for his/her studying | AnhVQHE153742 | 2023-10-06 | 22/05/2023
| Lesson List Edit | Course Content | This page shows the list of lessons for a selected package. On this page, the admin/expert is allowed to activate/deactivate, or call the Lesson Details for adding new or editing existing lesson | AnhVQHE153742 | 2023-10-06 | 22/05/2023
To do
Done
Doing

## Iter3
STT | Screen | Feature | Người chịu trách nghiệm | Trạng thái | Deadline | QUY TẮC LÀM VIỆC CỦA NHÓM 1.Mọi thành viên phải đăng ký account trên git hub bằng mail fpt.edu.vn 2.Tất cả thành viên phải thiết kế giao diện screen của mình trên figma 3.Mọi thành viên đều phải code 4.Các thành viên đều có nhiệm vụ đào tạo cho nhau để viết doc, code được. 5.Ai có khó khăn phải chia sẻ ngay với nhóm hoặc thầy 6. Tất cả các thành viên trong nhóm đều có cấu trúc thư mục dự án giống như thầy đã hướng dẫn. TL có trách nhiệm kiểm tra thành viên trong nhóm có cấu trúc thư mục như thầy hướng dẫn chưa và báo cáo vào nhóm. 7. TL tổ chức training các thành viên qua Ggmeet. Record lại buổi họp để chứng minh các thành viên đều được training và có tham gia 8. Không thể dựa vào trí nhớ của các thành viên mà hãy dựa vào các công cụ ghi chép : node, record,... để làm thành tài liệu, video tham khảo. 9. Mỗi tuần có 2 lần họp chính vào chủ nhật và thứ 5, nếu buổi học trên lớp các thành viên không đi đủ để thảo luận hoặc không có thời gian thảo luận trên lớp, tối hôm đó sẽ họp để tiến hành phân công nhiệm vụ, giờ họp cố định là 9h. 10. Nhiệm vụ được phân công cần được chia nhỏ theo ngày với deadline là 10h hằng ngày, mỗi khi xong nhiệm vụ thành viên cần thay đổi trạng thái nhiệm vụ thành chờ test, nhóm trưởng sẽ kiểm tra và thay đổi trạng thái thành đã hoàn thành hoặc fixing tùy theo mức độ hoàn thiện.
1 |  |  |  | To do
2 |  |  |  | To do
3 |  |  |  | To do
4 |  |  |  | To do
5 |  |  |  | To do
6 |  |  |  | To do
7 |  |  |  | To do
8 |  |  |  | To do
9 |  |  |  | To do
10 |  |  |  | To do
11 |  |  |  | To do
12 |  |  |  | To do
13 |  |  |  | To do
14 |  |  |  | To do
15 |  |  |  | To do
16 |  |  |  | To do
17 |  |  |  | To do
18 |  |  |  | To do
19 |  |  |  | To do
20 |  |  |  | To do
To do
Done
Doing

## Iter4
STT | Screen | Feature | Người chịu trách nghiệm | Trạng thái | Deadline | QUY TẮC LÀM VIỆC CỦA NHÓM 1.Mọi thành viên phải đăng ký account trên git hub bằng mail fpt.edu.vn 2.Tất cả thành viên phải thiết kế giao diện screen của mình trên figma 3.Mọi thành viên đều phải code 4.Các thành viên đều có nhiệm vụ đào tạo cho nhau để viết doc, code được. 5.Ai có khó khăn phải chia sẻ ngay với nhóm hoặc thầy 6. Tất cả các thành viên trong nhóm đều có cấu trúc thư mục dự án giống như thầy đã hướng dẫn. TL có trách nhiệm kiểm tra thành viên trong nhóm có cấu trúc thư mục như thầy hướng dẫn chưa và báo cáo vào nhóm. 7. TL tổ chức training các thành viên qua Ggmeet. Record lại buổi họp để chứng minh các thành viên đều được training và có tham gia 8. Không thể dựa vào trí nhớ của các thành viên mà hãy dựa vào các công cụ ghi chép : node, record,... để làm thành tài liệu, video tham khảo. 9. Mỗi tuần có 2 lần họp chính vào chủ nhật và thứ 5, nếu buổi học trên lớp các thành viên không đi đủ để thảo luận hoặc không có thời gian thảo luận trên lớp, tối hôm đó sẽ họp để tiến hành phân công nhiệm vụ, giờ họp cố định là 9h. 10. Nhiệm vụ được phân công cần được chia nhỏ theo ngày với deadline là 10h hằng ngày, mỗi khi xong nhiệm vụ thành viên cần thay đổi trạng thái nhiệm vụ thành chờ test, nhóm trưởng sẽ kiểm tra và thay đổi trạng thái thành đã hoàn thành hoặc fixing tùy theo mức độ hoàn thiện.
1 |  |  |  | To do
2 |  |  |  | To do
3 |  |  |  | To do
4 |  |  |  | To do
5 |  |  |  | To do
6 |  |  |  | To do
7 |  |  |  | To do
8 |  |  |  | To do
9 |  |  |  | To do
10 |  |  |  | To do
11 |  |  |  | To do
12 |  |  |  | To do
13 |  |  |  | To do
14 |  |  |  | To do
15 |  |  |  | To do
16 |  |  |  | To do
17 |  |  |  | To do
18 |  |  |  | To do
19 |  |  |  | To do
20 |  |  |  | To do
To do
Done
Doing